## Agile Sprint Backlog Group 3
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 | 8
Build Gui |  | Jarod | Complete | 6 | 5 | 4 | 3 | 1 | 0 | 0
Multiple Options in GUI |  | John | Complete | 5 | 4 | 3 | 1 | 1 | 1 | 0
Perimter |  | Isaac | Complete | 8 | 7 | 6 | 4 | 3 | 2 | 1
Learn Google ApI |  | Emily | Complete | 5 | 5 | 3 | 2 | 1 | 1 | 0
User Story #2 | 4
Update GUI to have perimter as option |  | John | Complete | 3 | 3 | 2 | 2 | 1 | 1 | 0
Redo the Sprint Backlog |  | Jarod | Complete | 2 | 1 | 0 | 0 | 0 | 0 | 0
Attach the perimter option to GUI |  | Emily | Complete | 5 | 4 | 3 | 3 | 2 | 1 | 0
Test the GUI |  | Isaac | Complete | 4 | 3 | 3 | 2 | 2 | 1 | 0
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 38 | 32 | 24 | 17 | 11 | 7 | 1